## Sheet1
ECEN 5823 - IoT Embedded Firmware
Course Project - Team 12
Test Plan
Sr. No. | Test to be performed | Expected Date | Actual Date | Test Result | Notes
1 | Test to check whether server is getting connected with client with an encrypted link | 2021-11-25 | 2021-12-06 | Passed
2 | Test to check whether the state machine implementation which is designed to take measurements and send it to the app is working correctly by using hard coded values to simulate. | 2021-11-24 | 2021-12-02 | Passed
3 | Test to check whether the Ultrasonic sensor that is being used is sending valid values back to the blue gecko board | 2021-11-24 | 2021-12-02 | Passed
4 | Test to check whether the stepper motor that is being used works properly after getting a signal from Gecko board. | 2021-11-26 | 2021-11-26 | Passed
5 | Test to check whether the blue gecko board is taking measurements only after indications are turned ON by the client. | 2021-11-26 | 2021-12-06 | Passed
6 | Test to check whether the stepper motor works after getting a value greater than the set threshold of Ultrasonic sensor. | 2021-11-28 | 2021-12-06 | Passed